## Sheet1
Project X Risk Register
| Positive Risk Response Options | Exploit | Share | Enhance | Accept
| Negative Risk Response Options | Avoid | Transfer | Mitigate | Accept
| Alternate Response Options | Contingency
Risk ID | Description | Cause | Effect | Risk Owner | Probability (1-5) | Impact (1-5) | PI Score | Expected Result, No Action | Risk Response Type | Response description
| Description of the risk | Cause of the risk | Effect on the project | Name of person who monitors the risk | Group sourced rough estimate of how likely this is to occur | Rough estimate of how significant the impact of this risk | Probability multiplied by Impact | What will happen if the risk becomes an issue and no action is taken | Decision made by group on how to respond to this risk (see above in blue) | How do you know it is time to put the response into play
1 | Tool Incompatibility | Benchmarking tools fail to work as needed | Delays in testing process | Miguel Ferreira | 2 | 4 | 8 | Testing will halt unexpectedly | Mitigate | Verify tool compatibility during the project setup phase; have backup tools ready for critical processes.
2 | Synthetic Data Bias | Limited Realist in synthetic datasets | Results may not represent real-world cases | Miguel Ferreira | 3 | 5 | 15 | Misleading conclusions | Mitigate | Use diverse datasets, including samples from publicly available APIs, to simulate multiple scenarios effectively.
3 | Protobuf Learning Curve | Complexity of Protocol Buffers | Incresed development time | Miguel Ferreira | 3 | 4 | 12 | Delays in experimental setup | Mitigate | Allocate time early in the project for team training and use official Protobuf resources/documentation.
4 | Network Instability | Unstable Network during testing | Skewed performance results | Miguel Ferreira | 2 | 5 | 10 | Unreliable test results | Mitigate | Use a controlled local environment for testing and benchmarking.
5 | Resource Constraints | Limited Access to computing rsources | Restricted testing scope | Miguel Ferreira | 3 | 4 | 12 | Missed opportunities for analysis | Mitigate | Plan experiments efficiently to minimize resource waste, and consider requesting additional computing time or infrastructure if necessary.
6 | Data Loss | Accidental deletion or corruption of data | Rework and delays | Miguel Ferreira | 2 | 5 | 10 | Loss of critical results | Avoid | Use version control for data and make regular backups throughout the project lifecycle.
7 | Software Bugs | Errors in benchmarking scripts | Skewed or invalid test results | Miguel Ferreira | 4 | 3 | 12 | Results will be unreliable | Mitigate | Perform code reviews and test scripts thoroughly before running full experiments.
8 | Time Constraints | Insufficient time allocated for experiments | Compromised quality of results | Miguel Ferreira | 3 | 5 | 15 | Critical steps may be rushed | Mitigate | Use a detailed timeline with milestones to monitor progress and ensure adequate time is allocated for experimentation.
9 | Changes in Tools Availability | Open-source tools become deprecated | Project delays | Miguel Ferreira | 2 | 3 | 6 | Rework on tools' compatibility | Mitigate | Continuously monitor tool development lifecycles and maintain a list of alternatives for all critical tools.
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0